## User stories
| Main User Story | Sub-Task
Team 1
1 | Login | enter email
enter password
valiadate mail
login with his id
2 | signup | enter all details
checks the mail
registers with capbook
3 | Forgot password | if user is existing can generate new password
4 | Homepage | user stoies will be visible
5 | change password | with mail id user can change password

## Swanand
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
1 | Questions
1.1 | Add Question
1.1.1 | Html Page | 3 | 3 | Saturday
1.1.2 | Component | 1 | 1 | Saturday
1.1.3 | Validations + Exception Handling | 1.5 | 1.5 | Tuesday
1.2 | Delete Question
1.2.1 | Html Page | 1 | 1 | Saturday
1.2.2 | Component | 1 | 1 | Saturday
1.2.3 | Validations + Exception Handling | 1.5 | 1.5 | Tuesday
1.3 | Update Question
1.3.1 | Html Page | 2 | 2 | Monday
1.3.2 | Component | 1.5 | 1.5 | Monday
1.3.3 | Validations + Exception Handling | 1.5 | 1.5 | Tuesday
1.4 | Show All Questions
1.4.1 | Html Page | 1 | 1 | Monday
1.4.2 | Component | 1 | 1 | Monday
1.4.3 | Validations + Exception Handling | 1.5 | 1.5 | Tuesday
1.5 | Registration + Login + Logout
1.5.1 | Html Page | 2 | 2 | Wednesday
1.5.2 | Component | 2 | 2 | Wednesday
1.5.3 | Validation | 1 | 1 | Wednesday
1.5.4 | Integration with backend | 1 | 1 | Wednesday

## Piyush
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
1 | User
1.1 | Update Profile
1.1.1 | Html Page | 2 | 2 | Saturday
1.1.2 | Component | 1 | 1 | Saturday
1.1.3 | Validations + Exception Handling | 2 | 2 | Wednesday
1.2 | Give Test
1.2.1 | Html Page | 1 | 1 | Monday
1.2.2 | Component | 1 | 1 | Monday
1.2.3 | Validations + Exception Handling | 0.5 | 0.5 | Monday
1.3 | Get Result
1.3.1 | Html Page | 1 | 1 | Monday
1.3.2 | Component | 1 | 1 | Monday
1.3.3 | Download Pdf | 3 | 3 | Monday
2 | Admin
2.1 | Update Profile
2.1.1 | Html Page | 1 | 1 | Saturday
2.1.2 | Component | 1 | 1 | Saturday
2.1.3 | Validations + Exception Handling | 1.5 | 1.5 | Wednesday
2.2 | Assign Test
2.2.1 | Html Page | 1 | 1 | Saturday
2.2.2 | Component | 1 | 1 | Saturday
2.2.3 | Validation | 1 | 1 | Wednesday
3 | Custom Error Pages
3.1 | Html Page | 2 | 2 | Wednesday
3.2 | Redirection | 3 | 2.5 | Wednesday

## Priya
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
1 | Test
1.1 | Add Test
1.1.1 | HTML Page | 3 | 3 | Saturday
1.1.2 | Component | 1 | 1 | Saturday
1.1.3 | Validations + Exception Handling | 2 | 2 | Saturday
1.2 | Show All Test
1.2.1 | HTML Page | 3 | 3 | Monday
1.2.2 | Component | 1.5 | 1.5 | Monday
1.2.3 | Validations + Exception Handling | 1.5 | 1.5 | Monday
1.3 | Remove Test
1.3.1 | HTML Page | 2 | 2 | Tuesday
1.3.2 | Component | 1.5 | 1.5 | Tuesday
1.3.3 | Validations + Exception Handling | 2 | 2 | Tuesday
1.4 | Update Test
1.4.1 | HTML Page | 2 | 2 | Wednesday
1.4.2 | Component | 1 | 1 | Wednesday
1.4.3 | Validations + Exception Handling | 2 | 2 | Wednesday